# Communications Action Plan

# July 2026-December 2028

# Purpose

This charter-style action plan guides the Advancing Together Communications Team, Black Hawk County Public Health (BHCPH), and partner organizations in implementing Economic Stability Strategy 11: educating community organizations on practices that improve the accessibility of publicly available materials. The plan is grounded in the Community Health Improvement Roadmap Summary and the communications worksheet, and it uses a quarterly structure to move from scoping and partner learning to practical tools, pilot implementation, and sustainability.

# Objective-Level Outcomes

| Outcome area | Charter outcome |
| --- | --- |
| Strategy and CHIP objective | Economic Stability Strategy 11: Educate community organizations on practices that improve the accessibility of publicly available materials, supporting the objective to strengthen community and system supports that improve economic stability for residents most affected by economic barriers by December 31, 2028. |
| By June 30, 2026 baseline | Action plan and success indicators are established for Strategy 11, with Advancing Together Communications Team roles and partner decision points documented. |
| By December 31, 2027 progress outcome | A practical toolkit/checklist, training model, resource hub, and first technical assistance cohort are in use by partner organizations. |
| By December 31, 2028 outcome | Partners have a sustainable quarterly process for improving public materials, tracking accessibility and language access practices, and updating shared resources as community needs change. |
| Measures to track | Organizations participating in training or technical assistance; organizations using the checklist/toolkit; public-facing materials reviewed or updated; priority languages identified for key materials; partner confidence and feedback; barriers needing funding or shared vendor support. |

# Quarterly Action Plan

| Quarter | Action to take | Responsible party(s) | Timeline | Key tasks | Resources | Success indicators |
| --- | --- | --- | --- | --- | --- | --- |
| Q1 | Convene the Advancing Together Communications Team to confirm the Strategy 11 charter and first-year decision points. | Advancing Together Communications Team; BHCPH Advancing Together Core Team; Jake and Gabbi; Northeast Iowa Food Bank and Pathways invited | Q1 (Jul-Sep 2026) | Confirm quarterly meeting rhythm; clarify whether the first phase centers on basic accessibility practices, language access, cultural review, or all three; document the intended audience for the first product. | Staff and volunteer meeting time; worksheet notes; CPA findings; shared agenda and documentation space. | Team confirms scope, meeting schedule, lead roles, and a short list of decisions needed by the end of Q2. |
| Q1 | Review Community Partner Assessment findings to identify priority barriers, languages, and public material types. | BHCPH data/convening staff; Advancing Together Communications Team; CPA participants as available | Q1 (Jul-Sep 2026) | Summarize translation, interpretation, accessibility, cost, time, technology, and staff capacity barriers; note common languages and areas with higher burden or people not currently reached. | CPA results; staff data time; partner knowledge about public-facing materials and service access barriers. | A short data brief identifies priority gaps, partner needs, and 3-5 material types to focus on first. |
| Q1-Q2 | Map existing communications infrastructure, authority, and resources that can support shared accessibility guidance. | BHCPH communications; Communications Hub team; Advancing Together Communications Team | Q1-Q2 (Jul-Sep 2026 through Oct-Dec 2026) | Inventory Google Drive, Facebook group, BHCPH Advancing Together webpage, draft Advancing Together website, partner channels, and local government accessibility lessons; clarify who can approve and maintain public-facing resources. | Communications staff time; current channels; shared file space; website or webpage support. | Resource map and maintenance owner options are documented before toolkit development begins. |
| Q2 | Hold targeted partner listening with organizations that understand language, disability, older adult, and low-literacy access barriers. | Advancing Together Communications Team; RIYO or other community-led groups; older adult, disability-serving, immigrant/refugee, library, school, and adult education partners | Q2 (Oct-Dec 2026) | Ask what would be most useful: training, toolkit, checklist, vendor list, peer examples, or online resource hub; gather examples of barriers created by online-only, small-print, untranslated, inaccessible PDF, video, image, or screenshot-only materials. | Meeting time; facilitation; interpretation or translation if needed; possible stipends for community reviewers; partner contact lists. | At least 8 partner or community reviewer perspectives inform the first product choice and quick-win practices. |
| Q2 | Select the first shared product and define practical success measures for partner use. | Advancing Together Communications Team; BHCPH Core Team; Northeast Iowa Food Bank; Pathways | Q2 (Oct-Dec 2026) | Choose whether to build a toolkit, checklist, decision tree, vendor/resource list, training, repository, or combined starter package; set realistic measures for partner learning and material updates. | Meeting time; CPA data brief; partner feedback; shared documentation template. | First shared product, audience, success measures, and development timeline are approved. |
| Q2-Q3 | Draft a beginner-friendly checklist and decision tree for public-facing materials. | BHCPH communications; Advancing Together Communications Team; local government communications partners | Q2-Q3 (Oct-Dec 2026 through Jan-Mar 2027) | Cover plain language, readability, accessible PDFs, websites, flyers, images, videos, social media posts, captions, alt text, large print, non-digital options, and public meeting materials; include quick wins such as avoiding screenshot-only flyers. | Staff drafting time; existing accessibility guidance; examples from Black Hawk County, Linn County, Johnson County, nonprofits, and community foundations. | Draft checklist and decision tree are ready for partner review by the end of Q3. |
| Q3 | Develop language access and cultural review guidance for translated materials. | Advancing Together Communications Team; immigrant/refugee-serving partners; trained bilingual staff or qualified interpreters/translators | Q3 (Jan-Mar 2027) | Identify priority language questions; explain when AI, Google Translate, bilingual staff, qualified translators, interpreters, or human cultural review may be appropriate; note risks, limits, and review steps. | Partner expertise; translation and interpretation vendor information; community reviewer time; possible stipends. | Guidance helps partners decide when translation, interpretation, or cultural review is needed for key materials. |
| Q3-Q4 | Create a shared vendor, tool, and example list for accessibility, translation, interpretation, captioning, and document support. | Advancing Together Communications Team; Community Foundation contacts; partner organizations willing to share vendors; web or communications vendors as available | Q3-Q4 (Jan-Mar 2027 through Apr-Jun 2027) | Collect vendors, tools, pricing considerations, turnaround times, accessibility reviewers, web developers, captioning options, and examples of strong local materials; flag where group pricing may be possible. | Staff research time; partner referrals; Community Foundation examples; vendor contacts; shared spreadsheet or repository. | Vendor/resource list includes at least 10 usable entries and notes cost, service type, and practical considerations. |
| Q4 | Pilot the draft toolkit with a small group of organizations before broader release. | Advancing Together Communications Team; Northeast Iowa Food Bank; Pathways; 3-5 pilot organizations | Q4 (Apr-Jun 2027) | Ask pilot organizations to apply the checklist to one flyer, webpage, PDF, social media post, video, or public meeting material; document what is clear, what is too burdensome, and what requires funding or technical assistance. | Pilot partner time; facilitation; checklist draft; technical assistance time; possible translation or accessibility review costs. | Pilot feedback produces concrete revisions and at least 3 materials are reviewed using the draft tool. |
| Q4 | Host the first training or peer-learning session on accessible, plain-language, and language-accessible public materials. | Advancing Together Communications Team lead; BHCPH communications; pilot partners as peer examples | Q4 (Apr-Jun 2027) | Share the starter checklist, quick wins, decision tree, and examples; include accessible print, digital, social media, translated, and non-digital communication practices. | Training time; meeting platform or venue; slides; partner examples; interpretation or captioning if needed. | At least 15 participants attend and post-session feedback shows increased confidence in creating accessible public materials. |
| Q5 | Launch a shared resource hub for accessibility, language access, and public material examples. | BHCPH communications; Communications Hub team; Advancing Together Communications Team | Q5 (Jul-Sep 2027) | Post the checklist, decision tree, vendor/tool list, training slides, quick-win examples, and contact path through Google Drive, the BHCPH Advancing Together webpage, and/or future Advancing Together website. | Website or file-space maintenance time; document formatting; link management; plain-language review. | Resource hub is live, shared through partner channels, and has an identified maintainer. |
| Q5-Q6 | Provide a first technical assistance cohort for organizations updating priority public materials. | Advancing Together Communications Team; BHCPH communications; partner volunteers with accessibility or language access expertise | Q5-Q6 (Jul-Sep 2027 through Oct-Dec 2027) | Support organizations in reviewing or revising materials that affect service access; prioritize plain language, readable layout, captions, alt text, accessible PDFs, translated materials, and non-digital options where needed. | Staff or volunteer technical assistance time; translation/accessibility review budget if available; shared templates; meeting time. | At least 6 organizations complete a material review and at least 10 public-facing materials are improved. |
| Q6 | Collect user and community reviewer feedback on whether revised materials reduce barriers to information access. | Pilot organizations; community reviewers; Advancing Together Communications Team | Q6 (Oct-Dec 2027) | Use brief feedback forms, partner conversations, or reviewer notes to assess clarity, language fit, readability, non-digital access, and usefulness for people not currently reached. | Feedback tool; reviewer time; possible stipends; interpretation or translation support. | Feedback identifies what changed, remaining barriers, and priorities for the next training cycle. |
| Q7 | Expand training and peer examples to a broader group of community organizations. | Advancing Together Communications Team; partner organizations; public libraries, schools/adult education providers, and nonprofit networks | Q7 (Jan-Mar 2028) | Offer a second session or peer-learning forum; highlight practical examples from the cohort; promote through existing partner channels; invite organizations with cost, training, translation, and technology barriers. | Training platform or venue; promotion time; updated toolkit; captions and interpretation if needed. | At least 25 additional participants are reached and 8 organizations commit to using the checklist or resource hub. |
| Q7-Q8 | Refresh toolkit content based on changing standards, partner use, and community language needs. | BHCPH communications; local government accessibility contacts; Advancing Together Communications Team | Q7-Q8 (Jan-Mar 2028 through Apr-Jun 2028) | Review changes in governmental accessibility timelines and lessons; update priority language information; remove outdated tools; add examples of accessible print, digital, video, and meeting materials. | Quarterly maintenance time; partner feedback; government accessibility updates; resource hub access. | Updated toolkit version is posted with a change log and partner notification. |
| Q8 | Explore shared funding, group pricing, or pooled vendor access for translation, interpretation, and accessibility support. | Advancing Together Communications Team; BHCPH Core Team; Community Foundation partners; interested nonprofits and vendors | Q8 (Apr-Jun 2028) | Assess partner demand, common service needs, likely costs, and possible funders; determine whether group rates, vendor agreements, or shared technical assistance are feasible. | Cost estimates; funder conversations; vendor discussions; partner demand survey; staff coordination time. | A feasibility memo identifies at least one viable shared resource or explains why individual partner approaches are more realistic. |
| Q9 | Institutionalize a quarterly communications accessibility touchpoint and reporting process. | Advancing Together Communications Team; BHCPH Advancing Together Core Team; coalition partners | Q9 (Jul-Sep 2028) | Add standing quarterly review of toolkit use, training reach, material updates, barriers, and partner needs; report progress to the Advancing Together coalition. | Quarterly meeting time; simple tracking spreadsheet; coalition agenda time; resource hub metrics if available. | Quarterly reporting process is in place and includes partner participation, materials updated, and barriers needing coalition attention. |
| Q10 | Complete the 2028 review and sustainability plan for shared communications accessibility resources. | Advancing Together Communications Team; BHCPH Core Team; key partner organizations | Q10 (Oct-Dec 2028) | Review accomplishments, partner feedback, materials updated, resource hub use, training reach, and remaining gaps; confirm 2029 ownership, maintenance, funding, and coalition reporting needs. | Evaluation time; partner feedback; tracking data; meeting time; sustainability planning template. | Final review documents progress and names owners, refresh schedule, and resource needs for sustaining the work beyond 2028. |

# Implementation Notes

Advancing Together will lead, convene, align, support, and track this strategy, while individual organizations retain responsibility for updating their own materials.

The first year should emphasize feasible practices that can be adopted by nonprofits and partner organizations with limited staff, time, and budget.

Shared tools should build from existing infrastructure, including the Communications Team, Google Drive, Facebook group, BHCPH Advancing Together webpage, Communication Hub team, partner channels, and any future Advancing Together website.

The plan should clarify practical lessons from governmental accessibility work without implying that all community organizations have the same legal obligations.

Translation and low-cost technology can help, but guidance should be clear about when human review, qualified interpreters/translators, or community reviewers are needed.

Quarterly work should focus on learning, piloting, updating real materials, and sustaining a simple system rather than creating a complex compliance program.

Implementation should remain practical and population-focused, with attention to areas with higher burden, barriers to care and services, older adults, people with disabilities, people with low literacy, people without reliable internet access, and people not currently reached by current communication practices.